## Sheet1
RENTAL MONITORING
ACTIVITIES |  | PLAN DATE | PLAN END | START DATE | END DATE | STATUS
PLANNING
Data Gathering | [5 empty] | DONE
AS-IS | [5 empty] | DONE
TO-BE | [5 empty] | DONE
ANALYZING
Story Board | [5 empty] | DONE
Database Schema/Design | [5 empty] | DONE
Create Database Tables
Initial Schema | [5 empty] | DONE
1st Revision: Rental Computer Purchase Date |  |  |  | 2018-07-25 | 2018-07-25 | DONE
DEVELOPMENT
Front-end
Working Module
Display, Filter | [5 empty] | DONE
Create Form
Basic Info | [5 empty] | DONE
Add/Edit/Delete Parts |  | 2018-07-23 | 2018-08-03 | 2018-07-23 | 2018-07-30 | DONE
Delivery View
Display, Filter | [5 empty] | DONE
Create Form
| Basic Info | 2018-08-06 | 2018-08-06 | 2018-07-30 | 2018-08-06 | DONE
Add/Edit/Return Rental Units |  | 2018-08-06 | 2018-08-13 | 2018-07-30 | 2018-08-06 | DONE
Print View |  |  |  |  | 2018-08-10 | DONE
Simpler Views
Accessory View | [5 empty] | DONE
Parts View | [5 empty] | DONE
Client View |  |  |  |  | 2018-08-13 | DONE
Report View
Deliveries per Month/Year (by release date) |  | 2018-08-14 | 2018-08-17 | 2018-08-14 | 2018-08-14 | DONE
Deliveries per Client |  | 2018-08-13 | 2018-08-14 | 2018-08-13 | 2018-08-14 | DONE
Rental Unit History |  | 2018-08-20 | 2018-08-31 | 2018-08-16 | 2018-08-16 | DONE
Projected Inventory (on hand+returning) |  | 2018-08-20 | 2018-08-31 | 2018-08-20 | 2018-08-22 | DONE
Security Roles
Access Control |  |  |  | 2018-08-20 | 2018-08-31
Viewer (viewing)
BDM (Viewer+reports)
Logistics (root privileges)
Testing(5 man-days)
GO-LIVE!